## Plan
Plan ID | Plan name | Date of export
2Dtqr42id0KV9LDIKajKBckAAhQZ | R26-IT-18 | 2026-10-14

## Consolidated Data
Task ID | Task Name | Bucket | Goal | Status | Priority | Assigned To | Created By | Created Date | Due date | Start date | Is Recurring | Late | Completed Date | Completed By | Completed Checklist Items | Checklist Items | Labels | Notes
zP5cMv-b8USVSkTvPvOpjMkAGA1g | Create Github Repo | To do |  | Completed | Medium | KOTHALAWALA L S S it22185884 | KOTHALAWALA L S S it22185884 | 2026-04-30 | 2026-04-30 | 2026-04-30 |  | false | 2026-04-30 | KOTHALAWALA L S S it22185884
tcIPZBks8UWtOgvptygoockAGKoo | Upload End of Month Progress Submission - April | To do |  | Completed | Medium | KOTHALAWALA L S S it22185884 | KOTHALAWALA L S S it22185884 | 2026-04-30 | 2026-04-30 | 2026-04-30 |  | false | 2026-08-28 | KOTHALAWALA L S S it22185884
-QboHi0_qE6KT22l6F6EbMkAFwnU | Upload End of Month Progress Submission - April | To do |  | Completed | Medium | MENDIS L.B.L it22197764 | KOTHALAWALA L S S it22185884 | 2026-04-30 | 2026-04-30 | 2026-04-30 |  | false | 2026-08-28 | KOTHALAWALA L S S it22185884
ZSu1OUfoaUKA-fzGjs53j8kAEzP5 | Upload End of Month Progress Submission - April | To do |  | Completed | Medium | THARAKA W.A.K.N it22211200 | KOTHALAWALA L S S it22185884 | 2026-04-30 | 2026-04-30 | 2026-04-30 |  | false | 2026-04-30 | KOTHALAWALA L S S it22185884
o-5sifg8zkmk_qfi2OXTa8kAGxkX | Upload End of Month Progress Submission - April | To do |  | Completed | Medium | Nawarathna I.K.K.R.B. it19131948 | KOTHALAWALA L S S it22185884 | 2026-04-30 | 2026-04-30 | 2026-04-30 |  | false | 2026-08-28 | KOTHALAWALA L S S it22185884
ZXxWwA_4yE-_2b_ZrnaatskAFVkj | Identify Goals and Objectives | Initiating |  | Completed | Medium | THARAKA W.A.K.N it22211200;Nawarathna I.K.K.R.B. it19131948;MENDIS L.B.L it22197764;KOTHALAWALA L S S it22185884 | KOTHALAWALA L S S it22185884 | 2026-05-05 |  |  |  | false | 2026-08-29 | KOTHALAWALA L S S it22185884 | 4/4 | Define project scope;Identify target users;Define project goals;Define primary objectives
OXHXeOq9lk-7QPtpJsGso8kAPbQF | Identify Stakeholders | Initiating |  | Completed | Medium | KOTHALAWALA L S S it22185884 | KOTHALAWALA L S S it22185884 | 2026-05-05 |  |  |  | false | 2026-08-29 | KOTHALAWALA L S S it22185884 | 2/2 | Define roles & responsibilities;Analyze stakeholder expectations
ep3doDtpVE-cXcQ9eInjP8kAMkDQ | Conduct Feasibility Study | Initiating |  | Completed | Medium | THARAKA W.A.K.N it22211200;Nawarathna I.K.K.R.B. it19131948;MENDIS L.B.L it22197764 | KOTHALAWALA L S S it22185884 | 2026-05-05 |  |  |  | false | 2026-08-29 | KOTHALAWALA L S S it22185884 | 3/3 | Operational feasibility;Financial feasibility;Technical feasibility
bKVbPuWrLkG6Jopf7rdNTskANBTa | Create Work Breakdown Structure | Planning |  | Completed | Medium | KOTHALAWALA L S S it22185884 | KOTHALAWALA L S S it22185884 | 2026-05-07 |  |  |  | false | 2026-08-29 | KOTHALAWALA L S S it22185884 | 3/3 | Divide project into modules;Assign responsibilities;Define deliverables
OjWhfizoWkW32ID1pCYPzckAP5uR | Develop Schedule & Timeline | Planning |  | Completed | Medium | THARAKA W.A.K.N it22211200;Nawarathna I.K.K.R.B. it19131948;MENDIS L.B.L it22197764;KOTHALAWALA L S S it22185884 | KOTHALAWALA L S S it22185884 | 2026-05-07 |  |  |  | false | 2026-08-29 | KOTHALAWALA L S S it22185884 | 3/3 | Define deadlines;Set milestones;Create Gantt chart
7ChvDbqVHUa6kUdknR89MMkAA8T2 | Identify Risks & Mitigation | Planning |  | Completed | Medium | THARAKA W.A.K.N it22211200;Nawarathna I.K.K.R.B. it19131948 | KOTHALAWALA L S S it22185884 | 2026-05-07 |  |  |  | false | 2026-08-29 | KOTHALAWALA L S S it22185884 | 3/3 | Identify possible risks;Define mitigation strategies;Risk impact analysis
aF3DiCoOAE2BM-KjA94xvckAETLy | Develop Budget | Planning |  | Completed | Medium | MENDIS L.B.L it22197764;KOTHALAWALA L S S it22185884 | KOTHALAWALA L S S it22185884 | 2026-05-07 |  |  |  | false | 2026-08-29 | KOTHALAWALA L S S it22185884 | 3/3 | Allocate resources;Estimate cost;Track expenses
FHmQt2HHhU29IS1keWsQMMkAPgGY | Develop & Integrate Components | Executing |  | Completed | Medium | THARAKA W.A.K.N it22211200;Nawarathna I.K.K.R.B. it19131948;MENDIS L.B.L it22197764;KOTHALAWALA L S S it22185884 | KOTHALAWALA L S S it22185884 | 2026-05-07 |  |  |  | false | 2026-08-29 | KOTHALAWALA L S S it22185884 | 4/4 | Database integration;Setup frontend;API development;Setup backend
yHp_BFnsREyC_OxfY-XEF8kAGr4s | Implement System Features | Executing |  | Completed | Medium | THARAKA W.A.K.N it22211200;Nawarathna I.K.K.R.B. it19131948;MENDIS L.B.L it22197764;KOTHALAWALA L S S it22185884 | KOTHALAWALA L S S it22185884 | 2026-05-07 |  |  |  | false | 2026-08-29 | KOTHALAWALA L S S it22185884 | 3/3 | UI/UX implementation;Feature testing;Core functionalities
X6lFw-U6-US7sTAx763R3MkANx4b | Connect Data Sources | Executing |  | Completed | Medium | THARAKA W.A.K.N it22211200;Nawarathna I.K.K.R.B. it19131948;MENDIS L.B.L it22197764;KOTHALAWALA L S S it22185884 | KOTHALAWALA L S S it22185884 | 2026-05-07 |  |  |  | false | 2026-08-29 | KOTHALAWALA L S S it22185884 | 3/3 | Setup database;Data validation;Connect APIs
WD538221lU6xsM-Vb0EkQskABp4O | Team Task Assignment | Executing |  | Completed | Medium | KOTHALAWALA L S S it22185884 | KOTHALAWALA L S S it22185884 | 2026-05-07 |  |  |  | false | 2026-08-29 | KOTHALAWALA L S S it22185884 | 3/3 | Update planner regularly;Assign tasks to members;Track task progress
vUvDxQB8Hkafi0XYllrXkckAI85e | Manage Changes | Monitoring & Controlling |  | Completed | Medium | THARAKA W.A.K.N it22211200;Nawarathna I.K.K.R.B. it19131948;MENDIS L.B.L it22197764;KOTHALAWALA L S S it22185884 | KOTHALAWALA L S S it22185884 | 2026-05-07 |  |  |  | false | 2026-08-29 | KOTHALAWALA L S S it22185884 | 3/3 | Adjust timeline;Update documentation;Handle requirement changes
SftcP0d3nUmYJk-OeKnNbskAK045 | Quality Assurance | Monitoring & Controlling |  | Completed | Medium | KOTHALAWALA L S S it22185884 | KOTHALAWALA L S S it22185884 | 2026-05-07 |  |  |  | false | 2026-08-29 | KOTHALAWALA L S S it22185884 | 3/3 | Performance checks;Bug fixing;Testing
EINzF8GCsUC-glp_H6yrXMkAKyx7 | Report Status | Monitoring & Controlling |  | Completed | Medium | THARAKA W.A.K.N it22211200;Nawarathna I.K.K.R.B. it19131948;MENDIS L.B.L it22197764;KOTHALAWALA L S S it22185884 | KOTHALAWALA L S S it22185884 | 2026-05-07 |  |  |  | false | 2026-08-29 | KOTHALAWALA L S S it22185884 | 3/3 | Share updates with team;Prepare monthly report;Track performance
1ji8xaMXB0-yaSDg6IU6z8kACh2b | Review Progress | Monitoring & Controlling |  | Completed | Medium | THARAKA W.A.K.N it22211200;Nawarathna I.K.K.R.B. it19131948;MENDIS L.B.L it22197764;KOTHALAWALA L S S it22185884 | KOTHALAWALA L S S it22185884 | 2026-05-07 |  |  |  | false | 2026-08-29 | KOTHALAWALA L S S it22185884 | 2/2 | Weekly progress check;Identify delays
HGKM8tKGf0mvxn8vejnniMkAKqOa | Archive Project | Closing |  | Not started | Medium |  | KOTHALAWALA L S S it22185884 | 2026-05-07 |  |  |  | false |  |  | 0/3 | Store source code;Backup documents;Final submission
YLZjvWI6GkSRdHWshTkAnMkADIX_ | Project Retrospective | Closing |  | Not started | Medium | THARAKA W.A.K.N it22211200;Nawarathna I.K.K.R.B. it19131948;MENDIS L.B.L it22197764;KOTHALAWALA L S S it22185884 | KOTHALAWALA L S S it22185884 | 2026-05-07 |  |  |  | false |  |  | 3/3 | Analyze project success;Team feedback;Identify lessons learned
_452xdM68UiRLvQyO8NRx8kAGAvy | Documentation | Closing |  | Not started | Medium | THARAKA W.A.K.N it22211200;Nawarathna I.K.K.R.B. it19131948;MENDIS L.B.L it22197764;KOTHALAWALA L S S it22185884 | KOTHALAWALA L S S it22185884 | 2026-05-07 |  |  |  | false |  |  | 2/3 | User guide;System documentation;API documentation
1zVMu40fXEigJsDD5VYWyskAJ5Wv | Deployment | Closing |  | Not started | Medium | THARAKA W.A.K.N it22211200;Nawarathna I.K.K.R.B. it19131948;MENDIS L.B.L it22197764;KOTHALAWALA L S S it22185884 | KOTHALAWALA L S S it22185884 | 2026-05-07 |  |  |  | false |  |  | 0/3 | Setup hosting;Final checks;Deploy system
oM4wVcP7PUC2UnFxEvpH_ckAEUvG | User Acceptance Testing | Closing |  | Not started | Medium | MENDIS L.B.L it22197764;KOTHALAWALA L S S it22185884 | KOTHALAWALA L S S it22185884 | 2026-05-07 |  |  |  | false |  |  | 2/3 | Collect feedback;Final improvements;Conduct UAT
OiAyK2jRY06JbjKg2oqiFckALxJc | List stakeholders | Initiating |  | Completed | Medium |  | KOTHALAWALA L S S it22185884 | 2026-08-29 |  |  |  | false | 2026-08-29 | KOTHALAWALA L S S it22185884
TJTWa_GvNUuJCZux60OL6MkAMQp7 | Final Presentation | Closing |  | Not started | Medium |  | KOTHALAWALA L S S it22185884 | 2026-10-14 | 2026-10-19 |  |  | false
V3Abe_eOgUKyjTgpwA5tMskAE7WA | Draft Thesis submission | Closing |  | Completed | Medium |  | KOTHALAWALA L S S it22185884 | 2026-10-14 | 2026-10-11 |  |  | false | 2026-10-14 | KOTHALAWALA L S S it22185884
vMRonQV_3USYX5aNRWj4BMkAJTAS | Website Submission | Closing |  | Completed | Medium |  | KOTHALAWALA L S S it22185884 | 2026-10-14 | 2026-10-11 |  |  | false | 2026-10-14 | KOTHALAWALA L S S it22185884
TRv_fbzjaUmi8qDxOybjTckAMWMv | Checklist Submission | Closing |  | Completed | Medium |  | KOTHALAWALA L S S it22185884 | 2026-10-14 | 2026-10-14 |  |  | false | 2026-10-14 | KOTHALAWALA L S S it22185884

## Tasks
Task ID | Task Name | Bucket | Goal | Status | Priority | Assigned To | Created By | Created Date | Due date | Start date | Is Recurring | Late | Completed Date | Completed By | Completed Checklist Items | Checklist Items | Labels | Notes
zP5cMv-b8USVSkTvPvOpjMkAGA1g | Create Github Repo | ZnPNs7zV-k6hI9zChvaZ-MkABeiy |  | Completed | Medium | d3df383d-33d3-4ad4-8d9c-483819252bc2 | d3df383d-33d3-4ad4-8d9c-483819252bc2 | 2026-04-30 | 2026-04-30 | 2026-04-30 |  | false | 2026-04-30 | d3df383d-33d3-4ad4-8d9c-483819252bc2
tcIPZBks8UWtOgvptygoockAGKoo | Upload End of Month Progress Submission - April | ZnPNs7zV-k6hI9zChvaZ-MkABeiy |  | Completed | Medium | d3df383d-33d3-4ad4-8d9c-483819252bc2 | d3df383d-33d3-4ad4-8d9c-483819252bc2 | 2026-04-30 | 2026-04-30 | 2026-04-30 |  | false | 2026-08-28 | d3df383d-33d3-4ad4-8d9c-483819252bc2
-QboHi0_qE6KT22l6F6EbMkAFwnU | Upload End of Month Progress Submission - April | ZnPNs7zV-k6hI9zChvaZ-MkABeiy |  | Completed | Medium | 1ecc7328-0483-4f59-9f1d-ecce2f0498bc | d3df383d-33d3-4ad4-8d9c-483819252bc2 | 2026-04-30 | 2026-04-30 | 2026-04-30 |  | false | 2026-08-28 | d3df383d-33d3-4ad4-8d9c-483819252bc2
ZSu1OUfoaUKA-fzGjs53j8kAEzP5 | Upload End of Month Progress Submission - April | ZnPNs7zV-k6hI9zChvaZ-MkABeiy |  | Completed | Medium | a4f9da14-52c0-4f89-b081-8d87df053d3f | d3df383d-33d3-4ad4-8d9c-483819252bc2 | 2026-04-30 | 2026-04-30 | 2026-04-30 |  | false | 2026-04-30 | d3df383d-33d3-4ad4-8d9c-483819252bc2
o-5sifg8zkmk_qfi2OXTa8kAGxkX | Upload End of Month Progress Submission - April | ZnPNs7zV-k6hI9zChvaZ-MkABeiy |  | Completed | Medium | 9204bd30-1fda-4235-bf65-aec67da13833 | d3df383d-33d3-4ad4-8d9c-483819252bc2 | 2026-04-30 | 2026-04-30 | 2026-04-30 |  | false | 2026-08-28 | d3df383d-33d3-4ad4-8d9c-483819252bc2
ZXxWwA_4yE-_2b_ZrnaatskAFVkj | Identify Goals and Objectives | CqogxY_qQkqXjqw0X0WQeMkAHVp4 |  | Completed | Medium | a4f9da14-52c0-4f89-b081-8d87df053d3f;9204bd30-1fda-4235-bf65-aec67da13833;1ecc7328-0483-4f59-9f1d-ecce2f0498bc;d3df383d-33d3-4ad4-8d9c-483819252bc2 | d3df383d-33d3-4ad4-8d9c-483819252bc2 | 2026-05-05 |  |  |  | false | 2026-08-29 | d3df383d-33d3-4ad4-8d9c-483819252bc2 | 4/4 | Define project scope;Identify target users;Define project goals;Define primary objectives
OXHXeOq9lk-7QPtpJsGso8kAPbQF | Identify Stakeholders | CqogxY_qQkqXjqw0X0WQeMkAHVp4 |  | Completed | Medium | d3df383d-33d3-4ad4-8d9c-483819252bc2 | d3df383d-33d3-4ad4-8d9c-483819252bc2 | 2026-05-05 |  |  |  | false | 2026-08-29 | d3df383d-33d3-4ad4-8d9c-483819252bc2 | 2/2 | Define roles & responsibilities;Analyze stakeholder expectations
ep3doDtpVE-cXcQ9eInjP8kAMkDQ | Conduct Feasibility Study | CqogxY_qQkqXjqw0X0WQeMkAHVp4 |  | Completed | Medium | a4f9da14-52c0-4f89-b081-8d87df053d3f;9204bd30-1fda-4235-bf65-aec67da13833;1ecc7328-0483-4f59-9f1d-ecce2f0498bc | d3df383d-33d3-4ad4-8d9c-483819252bc2 | 2026-05-05 |  |  |  | false | 2026-08-29 | d3df383d-33d3-4ad4-8d9c-483819252bc2 | 3/3 | Operational feasibility;Financial feasibility;Technical feasibility
bKVbPuWrLkG6Jopf7rdNTskANBTa | Create Work Breakdown Structure | FDYKVt_htUqWnsU7dejTWskAFaSI |  | Completed | Medium | d3df383d-33d3-4ad4-8d9c-483819252bc2 | d3df383d-33d3-4ad4-8d9c-483819252bc2 | 2026-05-07 |  |  |  | false | 2026-08-29 | d3df383d-33d3-4ad4-8d9c-483819252bc2 | 3/3 | Divide project into modules;Assign responsibilities;Define deliverables
OjWhfizoWkW32ID1pCYPzckAP5uR | Develop Schedule & Timeline | FDYKVt_htUqWnsU7dejTWskAFaSI |  | Completed | Medium | a4f9da14-52c0-4f89-b081-8d87df053d3f;9204bd30-1fda-4235-bf65-aec67da13833;1ecc7328-0483-4f59-9f1d-ecce2f0498bc;d3df383d-33d3-4ad4-8d9c-483819252bc2 | d3df383d-33d3-4ad4-8d9c-483819252bc2 | 2026-05-07 |  |  |  | false | 2026-08-29 | d3df383d-33d3-4ad4-8d9c-483819252bc2 | 3/3 | Define deadlines;Set milestones;Create Gantt chart
7ChvDbqVHUa6kUdknR89MMkAA8T2 | Identify Risks & Mitigation | FDYKVt_htUqWnsU7dejTWskAFaSI |  | Completed | Medium | a4f9da14-52c0-4f89-b081-8d87df053d3f;9204bd30-1fda-4235-bf65-aec67da13833 | d3df383d-33d3-4ad4-8d9c-483819252bc2 | 2026-05-07 |  |  |  | false | 2026-08-29 | d3df383d-33d3-4ad4-8d9c-483819252bc2 | 3/3 | Identify possible risks;Define mitigation strategies;Risk impact analysis
aF3DiCoOAE2BM-KjA94xvckAETLy | Develop Budget | FDYKVt_htUqWnsU7dejTWskAFaSI |  | Completed | Medium | 1ecc7328-0483-4f59-9f1d-ecce2f0498bc;d3df383d-33d3-4ad4-8d9c-483819252bc2 | d3df383d-33d3-4ad4-8d9c-483819252bc2 | 2026-05-07 |  |  |  | false | 2026-08-29 | d3df383d-33d3-4ad4-8d9c-483819252bc2 | 3/3 | Allocate resources;Estimate cost;Track expenses
FHmQt2HHhU29IS1keWsQMMkAPgGY | Develop & Integrate Components | My0JFRkBOEK6YfbZA8_SIMkAO2CV |  | Completed | Medium | a4f9da14-52c0-4f89-b081-8d87df053d3f;9204bd30-1fda-4235-bf65-aec67da13833;1ecc7328-0483-4f59-9f1d-ecce2f0498bc;d3df383d-33d3-4ad4-8d9c-483819252bc2 | d3df383d-33d3-4ad4-8d9c-483819252bc2 | 2026-05-07 |  |  |  | false | 2026-08-29 | d3df383d-33d3-4ad4-8d9c-483819252bc2 | 4/4 | Database integration;Setup frontend;API development;Setup backend
yHp_BFnsREyC_OxfY-XEF8kAGr4s | Implement System Features | My0JFRkBOEK6YfbZA8_SIMkAO2CV |  | Completed | Medium | a4f9da14-52c0-4f89-b081-8d87df053d3f;9204bd30-1fda-4235-bf65-aec67da13833;1ecc7328-0483-4f59-9f1d-ecce2f0498bc;d3df383d-33d3-4ad4-8d9c-483819252bc2 | d3df383d-33d3-4ad4-8d9c-483819252bc2 | 2026-05-07 |  |  |  | false | 2026-08-29 | d3df383d-33d3-4ad4-8d9c-483819252bc2 | 3/3 | UI/UX implementation;Feature testing;Core functionalities
X6lFw-U6-US7sTAx763R3MkANx4b | Connect Data Sources | My0JFRkBOEK6YfbZA8_SIMkAO2CV |  | Completed | Medium | a4f9da14-52c0-4f89-b081-8d87df053d3f;9204bd30-1fda-4235-bf65-aec67da13833;1ecc7328-0483-4f59-9f1d-ecce2f0498bc;d3df383d-33d3-4ad4-8d9c-483819252bc2 | d3df383d-33d3-4ad4-8d9c-483819252bc2 | 2026-05-07 |  |  |  | false | 2026-08-29 | d3df383d-33d3-4ad4-8d9c-483819252bc2 | 3/3 | Setup database;Data validation;Connect APIs
WD538221lU6xsM-Vb0EkQskABp4O | Team Task Assignment | My0JFRkBOEK6YfbZA8_SIMkAO2CV |  | Completed | Medium | d3df383d-33d3-4ad4-8d9c-483819252bc2 | d3df383d-33d3-4ad4-8d9c-483819252bc2 | 2026-05-07 |  |  |  | false | 2026-08-29 | d3df383d-33d3-4ad4-8d9c-483819252bc2 | 3/3 | Update planner regularly;Assign tasks to members;Track task progress
vUvDxQB8Hkafi0XYllrXkckAI85e | Manage Changes | mX8uJn9E00OXwqXLcGyJ78kAKeeu |  | Completed | Medium | a4f9da14-52c0-4f89-b081-8d87df053d3f;9204bd30-1fda-4235-bf65-aec67da13833;1ecc7328-0483-4f59-9f1d-ecce2f0498bc;d3df383d-33d3-4ad4-8d9c-483819252bc2 | d3df383d-33d3-4ad4-8d9c-483819252bc2 | 2026-05-07 |  |  |  | false | 2026-08-29 | d3df383d-33d3-4ad4-8d9c-483819252bc2 | 3/3 | Adjust timeline;Update documentation;Handle requirement changes
SftcP0d3nUmYJk-OeKnNbskAK045 | Quality Assurance | mX8uJn9E00OXwqXLcGyJ78kAKeeu |  | Completed | Medium | d3df383d-33d3-4ad4-8d9c-483819252bc2 | d3df383d-33d3-4ad4-8d9c-483819252bc2 | 2026-05-07 |  |  |  | false | 2026-08-29 | d3df383d-33d3-4ad4-8d9c-483819252bc2 | 3/3 | Performance checks;Bug fixing;Testing
EINzF8GCsUC-glp_H6yrXMkAKyx7 | Report Status | mX8uJn9E00OXwqXLcGyJ78kAKeeu |  | Completed | Medium | a4f9da14-52c0-4f89-b081-8d87df053d3f;9204bd30-1fda-4235-bf65-aec67da13833;1ecc7328-0483-4f59-9f1d-ecce2f0498bc;d3df383d-33d3-4ad4-8d9c-483819252bc2 | d3df383d-33d3-4ad4-8d9c-483819252bc2 | 2026-05-07 |  |  |  | false | 2026-08-29 | d3df383d-33d3-4ad4-8d9c-483819252bc2 | 3/3 | Share updates with team;Prepare monthly report;Track performance
1ji8xaMXB0-yaSDg6IU6z8kACh2b | Review Progress | mX8uJn9E00OXwqXLcGyJ78kAKeeu |  | Completed | Medium | a4f9da14-52c0-4f89-b081-8d87df053d3f;9204bd30-1fda-4235-bf65-aec67da13833;1ecc7328-0483-4f59-9f1d-ecce2f0498bc;d3df383d-33d3-4ad4-8d9c-483819252bc2 | d3df383d-33d3-4ad4-8d9c-483819252bc2 | 2026-05-07 |  |  |  | false | 2026-08-29 | d3df383d-33d3-4ad4-8d9c-483819252bc2 | 2/2 | Weekly progress check;Identify delays
HGKM8tKGf0mvxn8vejnniMkAKqOa | Archive Project | vVtQBOHRM0KuXvuYu9Qza8kAEIqp |  | Not started | Medium |  | d3df383d-33d3-4ad4-8d9c-483819252bc2 | 2026-05-07 |  |  |  | false |  |  | 0/3 | Store source code;Backup documents;Final submission
YLZjvWI6GkSRdHWshTkAnMkADIX_ | Project Retrospective | vVtQBOHRM0KuXvuYu9Qza8kAEIqp |  | Not started | Medium | a4f9da14-52c0-4f89-b081-8d87df053d3f;9204bd30-1fda-4235-bf65-aec67da13833;1ecc7328-0483-4f59-9f1d-ecce2f0498bc;d3df383d-33d3-4ad4-8d9c-483819252bc2 | d3df383d-33d3-4ad4-8d9c-483819252bc2 | 2026-05-07 |  |  |  | false |  |  | 3/3 | Analyze project success;Team feedback;Identify lessons learned
_452xdM68UiRLvQyO8NRx8kAGAvy | Documentation | vVtQBOHRM0KuXvuYu9Qza8kAEIqp |  | Not started | Medium | a4f9da14-52c0-4f89-b081-8d87df053d3f;9204bd30-1fda-4235-bf65-aec67da13833;1ecc7328-0483-4f59-9f1d-ecce2f0498bc;d3df383d-33d3-4ad4-8d9c-483819252bc2 | d3df383d-33d3-4ad4-8d9c-483819252bc2 | 2026-05-07 |  |  |  | false |  |  | 2/3 | User guide;System documentation;API documentation
1zVMu40fXEigJsDD5VYWyskAJ5Wv | Deployment | vVtQBOHRM0KuXvuYu9Qza8kAEIqp |  | Not started | Medium | a4f9da14-52c0-4f89-b081-8d87df053d3f;9204bd30-1fda-4235-bf65-aec67da13833;1ecc7328-0483-4f59-9f1d-ecce2f0498bc;d3df383d-33d3-4ad4-8d9c-483819252bc2 | d3df383d-33d3-4ad4-8d9c-483819252bc2 | 2026-05-07 |  |  |  | false |  |  | 0/3 | Setup hosting;Final checks;Deploy system
oM4wVcP7PUC2UnFxEvpH_ckAEUvG | User Acceptance Testing | vVtQBOHRM0KuXvuYu9Qza8kAEIqp |  | Not started | Medium | 1ecc7328-0483-4f59-9f1d-ecce2f0498bc;d3df383d-33d3-4ad4-8d9c-483819252bc2 | d3df383d-33d3-4ad4-8d9c-483819252bc2 | 2026-05-07 |  |  |  | false |  |  | 2/3 | Collect feedback;Final improvements;Conduct UAT
OiAyK2jRY06JbjKg2oqiFckALxJc | List stakeholders | CqogxY_qQkqXjqw0X0WQeMkAHVp4 |  | Completed | Medium |  | d3df383d-33d3-4ad4-8d9c-483819252bc2 | 2026-08-29 |  |  |  | false | 2026-08-29 | d3df383d-33d3-4ad4-8d9c-483819252bc2
TJTWa_GvNUuJCZux60OL6MkAMQp7 | Final Presentation | vVtQBOHRM0KuXvuYu9Qza8kAEIqp |  | Not started | Medium |  | d3df383d-33d3-4ad4-8d9c-483819252bc2 | 2026-10-14 | 2026-10-19 |  |  | false
V3Abe_eOgUKyjTgpwA5tMskAE7WA | Draft Thesis submission | vVtQBOHRM0KuXvuYu9Qza8kAEIqp |  | Completed | Medium |  | d3df383d-33d3-4ad4-8d9c-483819252bc2 | 2026-10-14 | 2026-10-11 |  |  | false | 2026-10-14 | d3df383d-33d3-4ad4-8d9c-483819252bc2
vMRonQV_3USYX5aNRWj4BMkAJTAS | Website Submission | vVtQBOHRM0KuXvuYu9Qza8kAEIqp |  | Completed | Medium |  | d3df383d-33d3-4ad4-8d9c-483819252bc2 | 2026-10-14 | 2026-10-11 |  |  | false | 2026-10-14 | d3df383d-33d3-4ad4-8d9c-483819252bc2
TRv_fbzjaUmi8qDxOybjTckAMWMv | Checklist Submission | vVtQBOHRM0KuXvuYu9Qza8kAEIqp |  | Completed | Medium |  | d3df383d-33d3-4ad4-8d9c-483819252bc2 | 2026-10-14 | 2026-10-14 |  |  | false | 2026-10-14 | d3df383d-33d3-4ad4-8d9c-483819252bc2

## Goals
Goal ID | Goal name | Status | Priority | Start date | Finish date | Connected tasks | Notes

## Buckets
Bucket ID | Bucket Name
ZnPNs7zV-k6hI9zChvaZ-MkABeiy | To do
CqogxY_qQkqXjqw0X0WQeMkAHVp4 | Initiating
FDYKVt_htUqWnsU7dejTWskAFaSI | Planning
My0JFRkBOEK6YfbZA8_SIMkAO2CV | Executing
mX8uJn9E00OXwqXLcGyJ78kAKeeu | Monitoring & Controlling
vVtQBOHRM0KuXvuYu9Qza8kAEIqp | Closing

## Users
User ID | User Name | Email
d3df383d-33d3-4ad4-8d9c-483819252bc2 | KOTHALAWALA L S S it22185884 | it22185884@my.sliit.lk
1ecc7328-0483-4f59-9f1d-ecce2f0498bc | MENDIS L.B.L it22197764 | it22197764@my.sliit.lk
a4f9da14-52c0-4f89-b081-8d87df053d3f | THARAKA W.A.K.N it22211200 | it22211200@my.sliit.lk
9204bd30-1fda-4235-bf65-aec67da13833 | Nawarathna I.K.K.R.B. it19131948 | it19131948@my.sliit.lk